## TEST PLAN
TEST PLAN
PROJECT NAME | Web Service Open to Malicious Attack
PROJECT ID | IAC IP25 - LP - Cybersecurity
INTERN NAME | Gaurav Jaywant Moynak
PROJECT MANAGER | Harshada Topale
INTRODUCTION
This document outlines the test strategy, methodology, scope, roles, objectives, and tools used in the Vulnerability Assessment and Penetration Testing (VAPT) project for the target URL: https://ccgac.bitrix24.site/. The purpose of this project is to identify, assess, and validate vulnerabilities in the web application using both manual and automated testing techniques.
SCOPE
IN SCOPE
Testing login mechanisms and password policies Scanning for exposed backup files or archives Attempting authentication bypass techniques Checking for unrestricted access to admin configurations Inspecting server headers, cookies, and CORS settings Testing web forms for XSS, CSRF, and input manipulation Evaluating load performance and DoS resilience Validating cache and connection stability Writing and demonstrating steganography techniquesConducting reconnaissance using DNS, WHOIS, and traceroute Inspecting public index files via Google Dorking Conducting directory brute-forcing Evaluating cookie security and HTTP headers Analyzing SSL/TLS configuration and cipher support
OUT SCOPE
Internal network scanning Social engineering attacks Phishing campaigns Physical security evaluation
QUALITY OBJECTIVE
Ensure the application meets functional and non-functional security requirements Verify adherence to secure development practices Detect and report any security flaws before public exposure
ROLES AND RESPONSIBILITIES
Intern: Conduct tests, document findings, provide PoC Manager: Ensure secure and stable test environments
TEST METHODOLOGY
OVERVIEW: Agile-based testing was used due to its flexibility and responsiveness to change. Testing activities were iterative, with findings validated and updated progressively. TEST LEVELS: System Testing Black Box Testing Manual and Automated Testing BUG TRIAGE: All bugs were logged, prioritized by severity (High, Medium, Low) Critical bugs scheduled for immediate patching Statuses were tracked in internal documentation TEST COMPLETENESS: 100% test coverage of defined audit points All manual and automated test cases executed All critical and major bugs fixed or recommended
TEST LEVELS (Define the Types of Testing to be executed on the Application Under Test (AUT))
Reconnaissance (Passive and Active) Vulnerability Scanning (Automated and Manual) Security Misconfiguration Testing Header and Cookie Inspection Performance and Load Testing Custom Code Evaluation (Python steganography)
BUG TRIAGE
All bugs were logged, prioritized by severity (High, Medium, Low) Critical bugs scheduled for immediate patching Statuses were tracked in internal documentation
TEST COMPLETENESS
100% test coverage of defined audit points All manual and automated test cases executed All critical and major bugs fixed or recommended
TEST DELIVERABLES
Test Plan (this document) Test Cases and Execution Logs Requirement Traceability Matrix Vulnerability Reports Final Audit Report Steganography Script and Output Client Validation and Sign-Off Sheet
RESOURCE AND ENVIRONMENT NEEDS
TESTING TOOLS
Dirsearch (directory brute forcing) Browser Developer Tools Burp Suite Community Edition Nikto Nmap curl, ping ApacheBench Wappalyzer (technology fingerprinting) Google Dorking via browser (search-based reconnaissance) Python (Pillow/Stegano for steganography)
TEST ENVIRONMENT
Kali Linux Chrome, Firefox, Edge Browsers Internet access for live site testing Python 3.10+ Office 2019+ for documentation
ADDITIONAL COMMENTS
The testing was carried out ethically and in coordination with stakeholders. All scans respected rate limits and terms of use. Missing security headers (HSTS, CSP, XFO) Weak cipher (3DES) and legacy TLS (1.0/1.1) Insecure cookie flags Cache-control misconfiguration
TEST PLAN
ITEMS TO TEST | TEST DESCRIPTION | TEST START DATE | TEST END DATE | RESPONSIBLE PERSON | STATUS | COMMENTS
Password Strength | Check for password complexity enforcement | 2025-08-04 | 2025-09-04 | Intern | Completed | Weak passwords allowed; no special char enforcement
Backup & Archiving | Search for public backup files | 2025-09-04 | 2025-10-04 | Intern | Completed | No exposed files found; Nikto confirms
Authentication Bypass | Attempt default creds, SQLi bypass | 2025-10-04 | 2025-11-04 | Intern | Completed | No bypass possible; forms protected
Admin Access w/o Login | Try accessing admin pages directly | 2025-11-04 | 2025-12-04 | Intern | Completed | All admin routes redirected to login page
Server Headers Check | Inspect server, cookies, and CORS headers | 13/04/2025 | 13/04/2025 | Intern | Completed | Missing some secure cookie flags
XSS/Form Tampering | Inject JS payloads and test CSRF | 14/04/2025 | 15/04/2025 | Intern | Completed | No reflected/stored XSS detected
Load Performance | Simulate requests using ApacheBench | 16/04/2025 | 17/04/2025 | Intern | Completed | Slowed after 200 concurrent requests
Code & Browser Inspection | Analyze JS/HTML code, test across browsers | 18/04/2025 | 18/04/2025 | Intern | Completed | Code is readable but lacks comments and standards
Cross-Platform Security | Test on mobile and desktop | 19/04/2025 | 19/04/2025 | Intern | Completed | Site works well on Chrome mobile and Edge desktop
DoS Protection Check | Try flooding login and form endpoints | 22/04/2025 | 23/04/2025 | Intern | Completed | No rate-limiting in place
Cache Configuration | Check cache-control and expiration headers | 25/04/2025 | 25/04/2025 | Intern | Completed | Some pages lacked cache-control headers
Connection Stability | Monitor timeouts and response delays | 29/04/2025 | 29/04/2025 | Intern | Completed | Mostly stable, minor delays under load
Steganography Program | Encode text into image using Python | 2025-05-05 | 2025-06-05 | Intern | Completed | Script and encoded output ready
Note on C17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To determine scope, you must – > Precise customer requirement > Project Budget > Product Specification > Skills & talent of your test team
Note on C24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The objective of the testing is finding as many software defects as possible; ensure that the software under test is bug free before release. To define the test objectives, you should do 2 following steps: > List all the software features (functionality, performance, GUI…) which may need to test. > Define the target or the goal of the test based on above features
Note on C40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A Testing Type is a standard test procedure that gives an expected test outcome. all Testing Types are aimed at achieving one common goal “Early detection of all the defects before releasing the product to the customer. There are tons of Testing Types for testing software product. Your team cannot have enough efforts to handle all kind of testing. As Test Manager, you must set priority of the Testing Types > Which Testing Types should be focused for web application testing? > Which Testing Types should be ignored for saving cost? The commonly used testing types are: 1. Unit Testing 2. API Testing 3. Integration Testing 4. System Testing 5. Install/Uninstall Testing 6. Agile Testing You need to decide based on your project scope, time and cost the testing type(s) required for your project
Note on C48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Test Criteria is a standard or rule on which a test procedure or test judgment can be based. There’re 2 types of test criteria as following Suspension Criteria Specify the critical suspension criteria for a test. If the suspension criteria are met during testing, the active test cycle will be suspended until the criteria are resolved. Exit Criteria It specifies the criteria that denote a successful completion of a test phase. The exit criteria are the targeted results of the test and are necessary before proceeding to the next phase of development. Example: 95% of all critical test cases must pass.