## Guide
IAC INTERNSHIP PROGRAM 2023
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Your Full Name
Document Created On: | DD-MMM-YYYY
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f

## EXAMPLE
PROJECT PLAN
Project Name | Web Application Open for malicious Attack
PROJECT SCOPE | To identify and assess security vulnerabilities in the web application and provide recommendations to improve its security.
PROJECT START DATE | 2025-09-03
PROJECT END DATE | 30/05/2025
OVERALL PROGRESS | Completed
SL NO | TASK NAME | START DATE | END DATE | DURATION IN DAYS | STATUS
| 1 Initiation | 2025-09-03 | 13/03/2025 | 5 | COMPLETED
| 1.1 Define project scope and objectives | 2025-09-03 | 13/03/2025 | 5 | COMPLETED
| 1.2 Identify stakeholders and resources | 2025-09-03 | 14/03/2025 | 6 | COMPLETED
| 1.3 Create project charter and get approvals | 2025-09-03 | 15/03/2025 | 7 | COMPLETED
| 1.4 Gather initial requirements and constraints | 2025-09-03 | 18/03/2025 | 5 | COMPLETED
| 2 Planning | 19/03/2025 | 23/03/2025 | 5 | COMPLETED
| 2.1 Develop detailed project plan and schedule | 19/03/2025 | 21/03/2025 | 3 | COMPLETED
| 2.2 Define team roles and assign responsibilities | 19/03/2025 | 21/03/2025 | 3 | COMPLETED
| 2.3 Identify tools and testing environment setup | 22/03/2025 | 26/03/2025 | 5 | COMPLETED
| 3 Execution | 27/03/2025 | 2025-06-05 | 41 | COMPLETED
| 3.1 Reconnaissance & Information Gathering | 27/03/2025 | 31/03/2025 | 5 | COMPLETED
| 3.2 Vulnerability Scanning and Enumeration | 2025-01-04 | 2025-07-04 | 7 | COMPLETED
| 3.2.1 DNS and Domain Analysis | 2025-01-04 | 2025-02-04 | 2 | COMPLETED
| 3.2.2 Network Scanning and Port Enumeration | 2025-03-04 | 2025-04-04 | 2 | COMPLETED
| 3.2.3 Web Application Fingerprinting | 2025-05-04 | 2025-07-04 | 3 | COMPLETED
| 3.3 Vulnerability Assessment and Analysis | 2025-08-04 | 16/04/2025 | 9 | COMPLETED
| 3.3.1 Manual Vulnerability Analysis | 2025-08-04 | 2025-12-04 | 5 | COMPLETED
| 3.3.2 Automated Scanning (using tools) | 13/04/2025 | 16/04/2025 | 4 | COMPLETED
| 3.4 Exploitation and Proof of Concept (PoC) | 17/04/2025 | 24/04/2025 | 8 | COMPLETED
| 3.5 Post-Exploitation and Privilege Escalation | 25/04/2025 | 29/04/2025 | 5 | COMPLETED
| 3.6 Reporting Vulnerabilities and Risk Analysis | 30/04/2025 | 2025-06-05 | 7 | COMPLETED
| 4 Testing & Validation | 2025-07-05 | 16/05/2025 | 10 | COMPLETED
| 4.1 Validate findings with client / retesting | 2025-07-05 | 2025-11-05 | 5 | COMPLETED
| 4.2 Finalize remediation recommendations | 2025-12-05 | 16/05/2025 | 5 | COMPLETED
| 5 Closure | 17/05/2025 | 30/05/2025 | 14 | COMPLETED
| 5.1 Prepare final audit report | 17/05/2025 | 23/05/2025 | 7 | COMPLETED
| 5.2 Presentation & project handover | 24/05/2025 | 27/05/2025 | 4 | COMPLETED
| 5.3 Project review and lessons learned | 28/05/2025 | 30/05/2025 | 3 | COMPLETED