## RAID LOG
| RAID Log | Should you face any difficulty in completing the RAID Log, please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f | [8 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 2 | 0 | 0 | 0 | 0 | 0 | Instruction to use the RAID log template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes. • Understand what risks, assumptions, issues, and dependencies are from the description provided in the methodology document • Select the category of RAID from the dropdown menu provided in the “RAID category” field in the template. • Provide a valid description of the RAID category that you have selected in the “description” field provided. • Describe the impact the RAID category you have selected will have on the project in the “impact field”. • Describe how the impact of the selected RAID category can be reduced on the project in the “mitigation field” in the template. • Mention the responsible person for working on the selected RAID category in the “owner” field in the template. • Select the priority with which the selected RAID category needs to be mitigated. The following levels of priority are given in the drop-down menu. Select; o Negligible: if the RAID category is not going to make an impact on the project o Low: if the raid category is going to make very small impacts on the project o Moderate: if the RAID category is going to make a few impacts which can affect the project adversely. o High: if the RAID category is going to make major impacts on the project adversely. o Critical: if the raid category is going to affect the project at any stage. • Provide risk priority number based on the priority selected for the RAID category selected. • Select the status of the RAID category selected. Two options are provided in the drop-down menu. Select; o Open: if the responsible person is still working on the RAID category selected. o Closed: if the responsible person has worked on the RAID category and is solved.
| Project title: | WEB SERVICE OPEN TO MALICIOUS ATTACKS |  | Project Id: | IAC IP25 | Project Manager: | Harshada Topale |  |  | Assumption | 1 | 0 | 0 | 0 | 0 | 0
[10 empty] | Issue | 1 | 0 | 0 | 0 | 0 | 0
| DOCUMENT VERSION: | 1 |  | Last Updated date: | 30/05/2025 | Project Team Lead: |  |  |  | Dependency | 1 | 0 | 0 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 5 |  |  |  |  | 0
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
2 | Risk | Limited access to some parts of the web application | Some vulnerabilities may be missed | Use available access fully; report access limitations in final report | Company / Project Team | High | 7 | Closed | Assumption
3 | Risk | Time constraints due to internship duration | Limited time for extensive testing | Prioritize critical tests; focus on high-risk areas | Company / Project Team | High | 8 | Closed | Issue
4 | Assumption | Website configuration remains stable during testing | Changes during testing could affect results | Perform tests in a short timeframe; document environment | Company / Project Team | Moderate | — | Closed | Dependency
5 | Issue | Some automated tools generated false positives | Wasted time verifying inaccurate vulnerabilities | Manually verify all automated findings | Company / Project Team | Moderate | — | Closed
6 | Dependency | Completion of testing depends on availability of target | Testing delays if site unavailable | Schedule tests when site is accessible; notify supervisor of delays | Company / Project Team | High | — | Closed | Open