## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | WEB SERVICE OPEN TO MALICIOUS ATTACKS
PROJECT ID | IAC IP25 - Cybersecurity
PROJECT MANAGER | Harshada Topale
PROJECT SPONSOR | Tushar Topale
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
1 | 2025-03-09 | Limited access to parts of the web app | Access Management | Yes | Request clearer access permissions earlier | Reported access limits and worked within scope | Company / Project Team | Solved | Affected thoroughness of vulnerability coverage
2 | 2025-03-15 | Time constraints during VAPT testing | Time Management | Yes | Prioritize critical vulnerabilities first | Focused on key risks; deferred low-risk testing | Company / Project Team | Solved | Helped complete testing within internship timeline
3 | 2025-03-18 | False positives from automated scans | Testing Accuracy | No | Manually verify tool findings before reporting | Cross-checked results and filtered false alarms | Intern | Solved | Improved report reliability
4 | 2025-03-20 | Minor changes on the website during tests | Environment Stability | No | Plan for environment stability during testing | Documented changes and retested impacted areas | Company / Project Team | Solved | No critical impact noted
5 | 2025-03-27 | Report formatting delays | Reporting Process | Yes | Use templates and allocate enough time for report | Followed company report format and submitted timely | Intern | Solved | Learned importance of proper documentatio